## Executive Summary
PRIYA GLOBAL — LAUNCH READINESS ASSESSMENT
As of March 7, 2026 — Based on Actual Code Audit
Metric | Value | Notes
Total Backend Services | 41 | All built, audited, syntax-verified
Total Backend Code | 51,455 lines | Python (FastAPI + asyncpg)
Shared Libraries | 16,790 lines | Security, caching, events, observability
Dashboard Pages | 13 pages | Next.js 14 + React 18 + TypeScript
Database Migrations | 10 files | Alembic-managed, PostgreSQL
Infrastructure (Terraform) | 5 modules | VPC, EKS, RDS, ElastiCache, MSK
Kubernetes Manifests | 9 files | Deployments, services, HPA, ingress, secrets
Docker Configs | 3 Dockerfiles + 4 compose | Base, service, dashboard
Security Audits Completed | 12 audits | All CRITICAL/HIGH findings fixed
Test Files | 141 files | 108 JS/TS + 33 Python
Overall Completion | 78% | Backend 95% ¦ Frontend 55% ¦ Infra 70% ¦ Ops 40%

## Service Inventory
# | Service | Port | Lines | Phase | Code Status | Security Audit | DB Schema | API Docs | Ready?
1 | API Gateway | 9000 | 1325 | P1 | Built & Audited | PASSED | N/A (proxy) | Yes | YES
2 | Auth Service | 9001 | 1460 | P1 | Built & Audited | PASSED | Migration 001 | Yes | YES
3 | Tenant Service | 9002 | 1500 | P1 | Built & Audited | PASSED | Migration 001 | Yes | YES
4 | Channel Router | 9003 | 1528 | P3 | Built & Audited | PASSED | Migration 001 | Yes | YES
5 | AI Engine (Brain v2) | 9004 | 2378 | P2 | Built & Upgraded | PASSED | Migration 001 | Yes | YES
6 | WhatsApp | 9010 | 1205 | P3 | Built & Audited | PASSED | Migration 001 | Yes | YES
7 | Email | 9011 | 1085 | P3 | Built & Audited | PASSED | Migration 001 | Yes | YES
8 | Voice (Twilio) | 9012 | 1158 | P3 | Built & Audited | PASSED | Migration 001 | Yes | YES
9 | Social (IG+FB) | 9013 | 963 | P3 | Built & Audited | PASSED | Migration 001 | Yes | YES
10 | WebChat Widget | 9014 | 840 | P3 | Built & Audited | PASSED | Migration 001 | Yes | YES
11 | SMS (Twilio) | 9015 | 1169 | P3 | Built & Audited | PASSED | Migration 007 | Yes | YES
12 | Telegram | 9016 | 1049 | P3 | Built & Audited | PASSED | Migration 001 | Yes | YES
13 | Billing (Stripe) | 9020 | 1321 | P1 | Built & Audited | PASSED (fixed) | Migration 001 | Yes | YES
14 | Analytics | 9021 | 1214 | P6 | Built & Audited | PASSED | Migration 001 | Yes | YES
15 | Marketing AI | 9022 | 1364 | P5 | Built & Audited | PASSED (fixed) | Migration 001 | Yes | YES
16 | E-Commerce | 9023 | 1355 | P4 | Built & Audited | PASSED | Migration 001 | Yes | YES
17 | Notification | 9024 | 1183 | P5 | Built & Audited | PASSED | Migration 001 | Yes | YES
18 | Plugin SDK | 9025 | 1112 | P7 | Built & Audited | PASSED | Migration 009 | Yes | YES
19 | Handoff | 9026 | 1265 | P5 | Built & Audited | PASSED (fixed) | Migration 001 | Yes | YES
20 | Leads & Pipeline | 9027 | 934 | P5 | Built & Audited | PASSED | Migration 001 | Yes | YES
21 | Conversation Intel | 9028 | 1146 | P5 | Built & Audited | PASSED (fixed) | Migration 001 | Yes | YES
22 | Appointments | 9029 | 1028 | P5 | Built & Audited | PASSED | Schema file | Yes | YES
23 | Knowledge Base | 9030 | 1054 | P3 | Built & Audited | PASSED (fixed) | Migration 001 | Yes | YES
24 | Voice AI (STT/TTS) | 9031 | 1210 | P3 | Built & Audited | PASSED | Migration 001 | Yes | YES
25 | Video Chat | 9032 | 628 | P3 | Built & Audited | PASSED | Migration 001 | Yes | YES
26 | RCS Messaging | 9033 | 864 | P3 | Built & Audited | PASSED | Migration 001 | Yes | YES
27 | Workflows | 9034 | 1172 | P5 | Built & Audited | PASSED | Migration 001 | Yes | YES
28 | Advanced Analytics | 9035 | 1007 | P6 | Built & Audited | PASSED | Migration 001 | Yes | YES
29 | AI Training | 9036 | 838 | P7 | Built & Audited | PASSED | Migration 001 | Yes | YES
30 | Marketplace | 9037 | 1025 | P7 | Built & Audited | PASSED | Migration 001 | Yes | YES
31 | Compliance/GDPR | 9038 | 1173 | P7 | Built & Audited | PASSED | Migration 003 | Yes | YES
32 | Health Monitor | 9039 | 1020 | P8 | Built & Audited | PASSED | Migration 001 | Yes | YES
33 | CDN Manager | 9040 | 673 | P8 | Built & Audited | PASSED (fixed) | Migration 001 | Yes | YES
34 | Deployment Mgr | 9041 | 842 | P8 | Built & Audited | PASSED | Migration 001 | Yes | YES
35 | Tenant Config | 9042 | 1531 | P6 | Built & Audited | PASSED | Migration 001 | Yes | YES
36 | Worker (Jobs) | 9043 | 469 | P8 | Built & Audited | PASSED | Migration 001 | Yes | YES
37 | Memory System | int | 1822 | P2 | Built & Audited | PASSED | Migration 005 | Yes | YES
38 | Translation | int | 1769 | P3 | Built & Audited | PASSED | Migration 004/006 | Yes | YES
39 | REST Connector | int | 1748 | P4 | Built & Audited | PASSED | Migration 008 | Yes | YES
40 | Developer Portal | int | 1534 | P7 | Built & Audited | PASSED | Migration 010 | Yes | YES
41 | Conversation | int | 648 | P2 | Built & Audited | PASSED | Migration 001 | Yes | YES
TOTAL | 41 Services | [7 empty] | 41/41 READY

## Done vs Not Done
Category | Item | Status | % Done | Gap / What's Missing | Priority for Launch
Backend Services | 41 Microservices (51,455 lines) | DONE | 100 | All built, audited, security-hardened | —
Backend Services | Shared Libraries (16,790 lines) | DONE | 100 | Security, caching, events, HTTP client, observability | —
Backend Services | AI Engine Brain v2.0 | DONE | 100 | Local classifier, ML scoring, dynamic confidence, single-call extraction | —
Backend Services | Multi-Tenant Isolation | DONE | 95 | Tenant_id enforced in all queries. 5% edge cases in webhook endpoints | LOW
Backend Services | Security Audit (all services) | DONE | 100 | 17 findings, 12 fixed, 5 noted (MEDIUM/LOW) | —
Database | PostgreSQL Schema (Alembic) | DONE | 90 | 10 migration files. Missing: lead_scoring_models table migration | MEDIUM
Database | Row-Level Security (RLS) | NOT DONE | 0 | RLS policies not implemented at DB level. App-level isolation only | HIGH
Database | Database Backup & Recovery | NOT DONE | 10 | Terraform has RDS config but no backup automation scripts | HIGH
Dashboard | Auth Pages (Login/Register) | DONE | 100 | NextAuth with JWT | —
Dashboard | Main Dashboard | DONE | 90 | Overview, stats, charts | LOW
Dashboard | Conversations Page | DONE | 85 | Real-time via WebSocket hooks | LOW
Dashboard | Customers Page | DONE | 85 | CRUD + search | LOW
Dashboard | Channels Page | DONE | 80 | Channel management | LOW
Dashboard | Handoffs Page | DONE | 80 | Agent queue management | LOW
Dashboard | Knowledge Base Page | DONE | 80 | Document upload + search | LOW
Dashboard | CSAT Page | DONE | 75 | Satisfaction metrics | LOW
Dashboard | Funnels Page | DONE | 75 | Conversion funnels | LOW
Dashboard | Settings Page | DONE | 70 | Tenant settings | MEDIUM
Dashboard | Onboarding Flow | DONE | 70 | Basic wizard. Needs polish for self-serve | HIGH
Dashboard | Analytics Page | NOT DONE | 0 | Backend exists (analytics service) but NO dashboard page | HIGH
Dashboard | Billing/Subscription Page | NOT DONE | 0 | Backend exists (billing service) but NO dashboard page | CRITICAL
Dashboard | Campaigns Page | NOT DONE | 0 | Backend exists (marketing service) but NO dashboard page | HIGH
Dashboard | Workflows Page | NOT DONE | 0 | Backend exists (workflows service) but NO dashboard page | MEDIUM
Dashboard | Marketplace Page | NOT DONE | 0 | Backend exists (marketplace service) but NO dashboard page | MEDIUM
Dashboard | Team Management Page | NOT DONE | 0 | No page for managing team members/roles | HIGH
Dashboard | API Keys/Developer Page | NOT DONE | 0 | Backend exists (developer_portal) but NO dashboard page | MEDIUM
Infrastructure | Docker (Dockerfile + compose) | DONE | 85 | 3 Dockerfiles, 4 compose files. Missing: production compose with replicas | MEDIUM
Infrastructure | Terraform (AWS) | DONE | 80 | VPC, EKS, RDS, ElastiCache, MSK modules. Budget-optimized | MEDIUM
Infrastructure | Kubernetes Manifests | DONE | 75 | Base deployment, services, HPA, ingress, secrets, network policy | MEDIUM
Infrastructure | PM2 Ecosystem Config | DONE | 100 | All 38 processes configured with ports | —
Infrastructure | Environment Config (.env) | DONE | 90 | .env.example with all variables documented | LOW
Operations | CI/CD Pipeline (GitHub Actions) | NOT DONE | 0 | No .github/workflows directory for Priya Global | CRITICAL
Operations | Monitoring (Prometheus/Grafana) | PARTIAL | 40 | docker-compose.tracing.yml + grafana/prometheus dirs exist. Not wired | HIGH
Operations | Sentry Error Tracking | DONE | 80 | Integrated in shared libs. Needs DSN configuration | MEDIUM
Operations | OpenTelemetry Tracing | DONE | 75 | Tracing middleware + otel-collector config exists | MEDIUM
Operations | Health Check Endpoints | DONE | 100 | All services have /health endpoint | —
Operations | Log Aggregation | NOT DONE | 10 | Structured logging exists but no ELK/CloudWatch pipeline | HIGH
Operations | Alerting & On-Call | NOT DONE | 0 | No PagerDuty/OpsGenie integration | MEDIUM
Compliance | GDPR Service Built | DONE | 85 | Compliance service (1,173 lines) with data export/deletion | LOW
Compliance | Privacy Policy / Terms | NOT DONE | 0 | No legal documents | CRITICAL
Compliance | SOC 2 Preparation | NOT DONE | 0 | Audit logging exists but no formal SOC 2 prep | LOW (post-launch)
Compliance | Data Processing Agreement | NOT DONE | 0 | Required for enterprise customers | MEDIUM
Go-to-Market | Marketing Website (priyaai.com) | NOT DONE | 0 | No website built | CRITICAL
Go-to-Market | Pricing Page | NOT DONE | 0 | Plans defined in code but no public pricing page | CRITICAL
Go-to-Market | API Documentation (public) | NOT DONE | 5 | OpenAPI specs exist in services but no hosted docs site | HIGH
Go-to-Market | Demo/Sandbox Environment | NOT DONE | 0 | No demo tenant for prospects | HIGH
Testing | Unit Tests | PARTIAL | 40 | 141 test files exist. Coverage unknown, likely <30% | MEDIUM
Testing | E2E Tests (Playwright) | PARTIAL | 20 | Playwright configured but minimal test coverage | HIGH
Testing | Load Testing | NOT DONE | 0 | No k6/locust scripts | HIGH
Testing | Integration Tests | NOT DONE | 10 | Some service-level tests but no cross-service integration tests | MEDIUM

## Launch Plan
Week | Dates | Phase | Tasks | Owner | Deliverable | Blocker?
Week 1 | Mar 10-14 | DASHBOARD (Critical) | 1. Build Billing/Subscription dashboard page 2. Build Analytics dashboard page 3. Build Team Management page | Claude + Dev | 3 dashboard pages Stripe integration visible | Stripe keys needed
Week 2 | Mar 17-21 | DASHBOARD (High) | 1. Build Campaigns/Marketing page 2. Build Workflows page 3. Polish Onboarding flow for self-serve 4. Build API Keys/Developer page | Claude + Dev | 4 more pages Onboarding polished
Week 3 | Mar 24-28 | DATABASE & CI/CD | 1. Implement PostgreSQL Row-Level Security (RLS) 2. Create lead_scoring_models migration 3. Build GitHub Actions CI/CD pipeline 4. Set up database backup automation | Claude | RLS policies active CI/CD running Backups scheduled | GitHub repo needed
Week 4 | Mar 31-Apr 4 | INFRA & MONITORING | 1. Wire Prometheus + Grafana dashboards 2. Configure Sentry DSN for all services 3. Set up log aggregation (CloudWatch/ELK) 4. Configure alerting (PagerDuty/email) | Claude + Dev | Full observability Alerting live | AWS access needed
Week 5 | Apr 7-11 | TESTING | 1. Write E2E tests for critical flows (onboarding, billing, messaging) 2. Load testing with k6 (target: 1000 concurrent tenants) 3. Cross-service integration tests 4. Security penetration test | Claude | Test suite Load test results Pen test report
Week 6 | Apr 14-18 | GO-TO-MARKET | 1. Build marketing website (priyaai.com) 2. Create pricing page with plan tiers 3. Host API documentation (Swagger/Redoc) 4. Create demo/sandbox tenant | Claude + Partner | Website live API docs hosted Demo available | Domain DNS setup
Week 7 | Apr 21-25 | LEGAL & COMPLIANCE | 1. Privacy Policy + Terms of Service 2. Data Processing Agreement template 3. GDPR compliance verification 4. Cookie consent + data deletion flow | Claude + Legal | Legal docs ready GDPR verified | Legal review needed
Week 8 | Apr 28-May 2 | AWS DEPLOYMENT | 1. Deploy to AWS EKS (ap-south-1 first) 2. Configure RDS PostgreSQL (Multi-AZ) 3. Set up ElastiCache Redis cluster 4. Configure MSK Kafka 5. SSL certificates + domain routing | Claude + Dev | Production infra live All services running on AWS | AWS billing approval
Week 9 | May 5-9 | SOFT LAUNCH (Beta) | 1. Onboard 3-5 beta tenants (invite-only) 2. Monitor performance & errors 24/7 3. Fix critical bugs found in beta 4. Gather feedback on UX/features | Team | Beta tenants active Feedback collected | Beta testers needed
Week 10 | May 12-16 | POLISH & SCALE | 1. Fix all beta feedback issues 2. Performance optimization based on real load 3. Add US/EU regions if demand exists 4. Final security audit | Claude + Dev | All fixes deployed Multi-region ready
Week 11 | May 19-23 | PUBLIC LAUNCH | 1. Open registration on priyaai.com 2. Product Hunt / Hacker News launch 3. Enable self-serve billing (Stripe live) 4. Activate marketing campaigns | Team | PRIYA GLOBAL IS LIVE | Marketing budget

## Cost to Launch
Item | Monthly Cost (USD) | Notes | Required Before Launch?
AWS EKS Cluster (3 t3.medium nodes) | 200 | Budget config from Terraform audit | YES
AWS RDS PostgreSQL (db.t3.medium) | 70 | Single-AZ budget, Multi-AZ = $140 | YES
AWS ElastiCache Redis (cache.t3.micro) | 15 | Single node, upgrade as needed | YES
AWS MSK Kafka (kafka.t3.small) | 60 | 2-broker minimum | YES
AWS S3 + CloudFront (CDN) | 10 | Media storage + CDN delivery | YES
AWS Route 53 (DNS) | 2 | Hosted zone + queries | YES
AWS CloudWatch (Logs) | 15 | Log ingestion + retention | YES
Domain (priyaai.com) | 1 | $12/year | YES
SSL Certificate (ACM) | 0 | Free with AWS | YES
Stripe Fees | 0 | 2.9% + 30¢ per transaction (pass-through) | YES
Anthropic API (Claude) | 100 | ~$0.003/msg × 33K msgs/month estimate | YES
OpenAI API (fallback) | 30 | Secondary LLM for cost optimization | NO
Sentry (Error Tracking) | 0 | Free tier: 5K events/month | YES
GitHub (Repository) | 0 | Free for private repos | YES
Twilio (SMS/Voice) | 50 | Pay-per-use, $50 starting credit | YES (if SMS/Voice enabled)
Meta (WhatsApp Business) | 0 | Free tier: 1000 conversations/month | YES
PagerDuty/OpsGenie | 0 | Free tier for small team | NO
TOTAL MONTHLY (Budget)
TOTAL MONTHLY (Comfortable) |  | Bare minimum to run
With 30% buffer for scaling

## ClickUp Pending
Phase | Task | Status | Required for Launch? | Week to Complete
Phase 0 | Define Global System Architecture | TO DO | Already built (code exists) | —
Phase 0 | Design Multi-Tenant DB Architecture | TO DO | Already built (code exists) | —
Phase 0 | Design API Contract & OpenAPI Specs | TO DO | Partially exists in services | Week 6
Phase 0 | Event-Driven Architecture & Message Bus | TO DO | Already built (Kafka + EventBus) | —
Phase 0 | AWS Infrastructure Blueprint | TO DO | Terraform exists, needs review | Week 4
Phase 0 | Security Architecture & Compliance | TO DO | 12 audits done, need formal doc | Week 7
Phase 0 | Automated Security Audit (SAST) | TO DO | Manual audits done, need CI integration | Week 3
Phase 0 | SEC: Switch to Multi-AZ | TO DO | Terraform config ready, needs apply | Week 8
Phase 0 | SEC: RDS Backup Retention 7+ Days | TO DO | Terraform variable change | Week 8
Phase 0 | SEC: VPC Flow Logs | TO DO | Terraform addition needed | Week 8
Phase 0 | SEC: EKS Public API CIDR Whitelist | TO DO | Terraform addition needed | Week 8
Phase 1 | DB Migration: SQLite → PostgreSQL | TO DO | Alembic migrations exist | Week 3
Phase 1 | CI/CD Pipeline (GitHub Actions) | TO DO | CRITICAL — No pipeline exists | Week 3
Phase 2 | Multi-LLM Router | TO DO | AI Engine has Claude, needs fallback routing | Week 2
Phase 8 | Marketing Website (priyaai.com) | TO DO | CRITICAL — No website | Week 6
Phase 8 | Multi-Region AWS Deployment | TO DO | Start with 1 region, expand later | Post-launch
Phase 8 | Performance Optimization & Load Testing | TO DO | Need k6/locust scripts | Week 5
Phase 8 | Onboarding Flow & Self-Serve | TO DO | Basic page exists, needs polish | Week 2
Phase 8 | Monitoring, Alerting, On-Call | TO DO | Grafana/Prometheus dirs exist | Week 4
Phase 8 | SOC 2 Certification Prep | TO DO | Post-launch priority | Post-launch
Phase 8 | GDPR Compliance Implementation | TO DO | Service built, needs verification | Week 7